## Read me
Change register template
From Enco Group (enco.au)
What this is | The record that management of change happened: one row per change, with its class, the reviews it needed, the approval and its conditions, the documents to update, the pre-startup check and the close-out, and for temporary changes the expiry.
The test | The design basis moved or it did not. A replacement in kind goes on a work order. Anything else is a change at a class that fits its size. The Classification sheet gives the tests.
How to use it | Number every request. Classify it before anything else. Set the reviews required from the class, not from who is available. Do not close a change until every document that described the old state has been reissued and the pre-startup check is signed. Read the open rows first at the weekly review, and the expired temporary changes before those. The three example rows are a minor replacement, an interlock change and a temporary bypass; delete them before use. The steps and the reasoning are at https://enco.au/articles/management-of-change-plant-modifications
Terms of use | Free to use and adapt. Provided as a starting point, without warranty, and not a substitute for a site's own management of change procedure or its process safety obligations.
Column | What goes in it
Change number | Never reused
Title | As it says
Requested by, date | As it says
Equipment and area | The tags and the area, so the change can be found from the asset
What and why | The change and the reason, in enough words to review
Class | As it says (drop-down: Replacement in kind, Minor, Change, Temporary, Procedural, Organisational, Emergency)
Reviews required | From the class
Hazard review | The study the class requires, or none with the reason
Approved by, date | The authority for the class
Conditions | What the approval depends on
Expiry | Temporary changes only
Documents to update | Drawings, datasheets, procedures, job plans, alarms, the CMMS
Updates done | As it says (drop-down: Y, N)
Pre-startup check by, date | As it says
Status | As it says (drop-down: Requested, In review, Approved, Rejected, Implemented, Closed, Expired)
Closed by, date | As it says

## Register
Change number | Title | Requested by, date | Equipment and area | What and why | Class | Reviews required | Hazard review | Approved by, date | Conditions | Expiry | Documents to update | Updates done | Pre-startup check by, date | Status | Closed by, date
MOC-2026-031 | Replace CV-201 head pulley bearings with a different maker's equivalent | Planner, 2026-08-04 | CV-201-M1, area 200 | Original bearings on twenty-week lead. Proposed equivalent is the same ISO designation and C3 clearance. Confirm fit, load rating and seal arrangement. | Minor | Mechanical engineering | None: like for like by specification | Mechanical lead, 2026-08-06 | Datasheet and bill of materials updated; store code added |  | DS-CV-201-M1, BOM, job plan JP-ME-041 | Y | Supervisor, 2026-08-12 | Closed | Planner, 2026-08-14
MOC-2026-044 | Add a second belt drift switch at the CV-201 tail and change the trip logic to either switch | Reliability, 2026-10-02 | CV-201, area 200 | Three drift trips this year were at the tail where there is no switch. Add ZS-201B and change the interlock to trip on either. | Change | Mechanical, electrical, control, operations | Interlock review against the cause and effect | Engineering manager, 2026-10-09 | Loop diagram and cause and effect reissued before start-up; alarm rationalised; operators briefed |  | LOOP-0117, CE-0002, PLC backup, alarm database, operating procedure | N |  | Implemented
MOC-2026-047 | Temporary bypass of CR-001 lube oil filter differential trip while the transmitter is replaced | Supervisor, 2026-10-21 | CR-001-LUB, area 100 | Transmitter failed. Bypass the trip for 48 hours with a manual check each shift until the replacement is fitted. | Temporary | Control, operations, safety | Risk assessment for the bypass period | Operations manager, 2026-10-21 | Manual differential check each shift logged; bypass tag on the panel | 2026-10-23 | Bypass register, shift log | Y | Supervisor, 2026-10-21 | Closed | Supervisor, 2026-10-23
A temporary change past its expiry with a status other than Closed is a finding. Reverse it, or extend it through the same steps.
Note on A1: Never reused
Note on D1: The tags and the area, so the change can be found from the asset
Note on E1: The change and the reason, in enough words to review
Note on G1: From the class
Note on H1: The study the class requires, or none with the reason
Note on I1: The authority for the class
Note on J1: What the approval depends on
Note on K1: Temporary changes only
Note on L1: Drawings, datasheets, procedures, job plans, alarms, the CMMS

## Classification
The proposal | Classification | What follows
Same make, model, rating and material, fitted the same way | Replacement in kind | Work order only
A different make or model with the same function, rating and material | Change, minor | Engineering check that the specification is met, drawings and datasheets updated
A different rating, material, size or setting | Change | Full review, because the design basis has moved
A new or removed interlock, alarm, setpoint or logic | Change | Full review with the control narrative and the hazard study
A new or changed procedure that alters a step, a limit or a hazard | Change, procedural | Operations and safety review, training before use
A temporary bypass, jumper, blank or override | Temporary change | Full review, an expiry date, and a reversal recorded
A change to who does what, or to the organisation around the plant | Organisational change | Review of the competence and the handover, which is often missed

## Steps
Step | What it does | What it produces
Request | Anyone proposes a change, in writing, with what, why and the equipment affected | A numbered request in the register
Classify | Is it a change at all, or a replacement in kind? If a change, what kind, and how much review does it need? | Replacement in kind closed here; a change given a class and a review path
Review | The disciplines affected assess it: engineering, operations, maintenance, safety, environment, and the hazard review the class requires | Findings and conditions, each with an owner
Approve | A named authority for the class accepts the change with its conditions, or rejects it | An approval with conditions, or a rejection with a reason
Implement | The change is made as approved, with temporary changes given an expiry date | The change in place, the conditions met
Update | Drawings, the register, the CMMS, spares, procedures, job plans, alarms and the control system backup brought into line | Every record that described the old state now describes the new
Verify and start | A pre-startup check that the change matches the approval and the updates are done; training delivered | Start-up authorised
Close | The change closed in the register with its evidence; temporary changes reversed or made permanent through the same steps | A closed record, or a reopened one