## Read me
IO list and cause and effect template
From Enco Group (enco.au)
What this is | The two control system design documents the tests are run from. The IO list has one row per input and output with its tag, type, signal, range, controller address, wiring, alarms and loop drawing. The cause and effect matrix has the causes down the side, the effects across the top and a mark where a cause produces an effect.
The rule | The IO list is built from the P&ID and the instrument index, and the matrix is the master for interlocks: a change to an interlock is made on the matrix, reviewed there, and only then coded.
How to use it | Fill the IO list from the P&ID, one row per point, and keep the status column current through the factory and site acceptance tests. On the Cause and effect sheet put T for a trip, A for an alarm only, and leave the cell blank for nothing, with a note where a trip has a delay or a start inhibit. The eight IO rows and six causes are a conveyor's; delete them before use. The document chain and the reasoning are at https://enco.au/articles/control-system-design-documents
Terms of use | Free to use and adapt. Provided as a starting point, without warranty, and not a substitute for a site's own engineering standards or its process safety obligations.
IO list column | What goes in it
Tag | From the P&ID, ISA-5.1 style or the site's standard
Description | Service and function, in words
Area / system | As it says
P&ID | The drawing it appears on
IO type | As it says (drop-down: AI, AO, DI, DO, Comms)
Signal | 4-20 mA, HART, 24 V DC dry contact, Profinet, Modbus TCP and so on
Range and units | Analogue: the calibrated range and the engineering units. Discrete: the state when true
Controller | As it says
Rack / slot / channel | Where it lands
Cable | From the cable schedule
Junction box | As it says
Alarm | The alarms configured on it, with priority
Interlock ref | The cause and effect row or column it appears in
Loop drawing | As it says
Status | As it says (drop-down: Design, Wired, FAT passed, Loop checked, Spare, Deleted)

## IO list
Tag | Description | Area / system | P&ID | IO type | Signal | Range and units | Controller | Rack / slot / channel | Cable | Junction box | Alarm | Interlock ref | Loop drawing | Status
ZS-201A | CV-201 belt drift switch, head end, drive side | 200 / CV-201 | PID-2003 | DI | 24 V DC dry contact | True = drift | PLC-200 | R1 / S3 / 07 | C-2041 | JB-2004 | Drift, priority 2 | C&E row 2 | LOOP-0117 | Loop checked
ZS-201B | CV-201 belt drift switch, tail end | 200 / CV-201 | PID-2003 | DI | 24 V DC dry contact | True = drift | PLC-200 | R1 / S3 / 08 | C-2042 | JB-2006 | Drift, priority 2 | C&E row 2 | LOOP-0118 | Loop checked
ZS-201C | CV-201 pull-wire switch, full length | 200 / CV-201 | PID-2003 | DI | 24 V DC dry contact, fail safe | True = healthy | PLC-200 | R1 / S3 / 09 | C-2043 | JB-2004 | Pull-wire, priority 1 | C&E row 1 | LOOP-0119 | Loop checked
SS-201 | CV-201 underspeed switch, tail pulley | 200 / CV-201 | PID-2003 | DI | 24 V DC dry contact | True = speed OK | PLC-200 | R1 / S3 / 10 | C-2044 | JB-2006 | Underspeed, priority 2 | C&E row 3 | LOOP-0120 | Loop checked
TE-201 | CV-201 drive gearbox bearing temperature | 200 / CV-201 | PID-2003 | AI | 4-20 mA, Pt100 head transmitter | 0 to 150 degrees C | PLC-200 | R1 / S5 / 02 | C-2045 | JB-2004 | High 85 priority 3, high high 95 priority 2 | C&E row 4 | LOOP-0121 | Loop checked
LSH-201 | CV-201 head chute blocked chute switch | 200 / CV-201 | PID-2003 | DI | 24 V DC dry contact | True = blocked | PLC-200 | R1 / S3 / 11 | C-2046 | JB-2004 | Blocked chute, priority 1 | C&E row 5 | LOOP-0122 | Loop checked
WT-201 | CV-201 belt weigher, rate and total | 200 / CV-201 | PID-2003 | Comms | Modbus TCP from the weigher integrator | 0 to 1,500 t/h; total in t | PLC-200 | Ethernet port 2 | F-2010 |  | None |  | NET-2001 | FAT passed
XV-201 | CV-201 drive run command | 200 / CV-201 | PID-2003 | DO | 24 V DC to the VSD run input | True = run | PLC-200 | R1 / S4 / 01 | C-2047 |  | None | C&E column A | LOOP-0123 | Loop checked
Note on A1: From the P&ID, ISA-5.1 style or the site's standard
Note on B1: Service and function, in words
Note on D1: The drawing it appears on
Note on F1: 4-20 mA, HART, 24 V DC dry contact, Profinet, Modbus TCP and so on
Note on G1: Analogue: the calibrated range and the engineering units. Discrete: the state when true
Note on I1: Where it lands
Note on J1: From the cable schedule
Note on L1: The alarms configured on it, with priority
Note on M1: The cause and effect row or column it appears in

## IO count
IO type | Points
AI
AO
DI
DO
Comms
Total
Counted from the IO list, excluding rows marked Deleted. Spare points are counted so the rack has room for them.

## Cause and effect
Cause and effect matrix |  | Effects →
Cause ↓ | Tag | Stop CV-201 | Inhibit CR-001 feed | Stop upstream sequence | Alarm to operator | Inhibit restart until reset | Note
Pull-wire operated | ZS-201C | T | T | T | A | T | Hardwired to the drive as well as through the PLC
Belt drift, either switch | ZS-201A/B | T | T | T | A | T | Either switch, after MOC-2026-044
Underspeed after start delay | SS-201 | T | T | T | A |  | 10 s start delay before the check is armed
Gearbox bearing temperature high high | TE-201 > 95 | T | T |  | A |  | High at 85 is alarm only
Head chute blocked | LSH-201 | T | T | T | A | T | Stops the belt before the chute fills
Downstream CR-001 stopped | CR-001 run = false | T |  | T | A |  | Sequence stop, not a trip: belt runs out first
T = trip or stop. A = alarm only. Blank = no effect. Add effects as columns and causes as rows; every mark that is not a plain trip gets a note.

## Documents
Document | What it says | Built from | Used for | Owner
P&ID | The process: equipment, lines, instruments and control functions, with every tag | The process design | Everything below starts from it | Process engineering
Control philosophy | The principles: the control system architecture, the modes of operation, how alarms, interlocks, permissives and sequences are to be handled, naming and numbering | The P&ID and the site's standards | The frame the narrative and the HMI design sit inside | Control engineering
Functional design specification | The control narrative: what each system does in words, loop by loop and sequence by sequence, in every mode and on every abnormal path | The P&ID and the philosophy, with operations | The programmer codes from it, the FAT tests against it, operations learn the plant from it | Control engineering
Cause and effect matrix | Every interlock and trip as a grid: each cause, each effect, and the mark where a cause produces an effect | The narrative and the hazard studies | The one page a reviewer, a programmer and a tester can all check | Control engineering, with process safety where it applies
Alarm philosophy | How alarms are chosen, prioritised, presented and reviewed | The site's alarm standard | Rationalisation, the master alarm database, the HMI | Operations and control engineering
IO list | Every input and output: tag, type, signal, range, where it lands in the controller and what it is wired through | The P&ID and the instrument index | Panel design, the loop diagrams, the IO check at FAT and the loop check at SAT | Control engineering
Instrument index | Every instrument with its service, type, range, make and model, datasheet and loop | The P&ID | Procurement, calibration, the loop diagrams, the asset register | Instrument engineering
Loop diagrams | One drawing per loop from the field device to the controller: terminals, cores, junction boxes, cables, power | The IO list, the instrument index and the panel drawings | Installation, the loop check, and every fault found afterwards | Electrical and control
Network and architecture drawings | The controllers, servers, switches, links and protocols, and the zones between them | The philosophy and the security design | Installation, the SAT communications tests, OT security | Control and IT
HMI design and graphics | The display hierarchy, the graphics standard, the navigation, the permissions, the displays themselves | The philosophy, the P&ID and the alarm philosophy | What the operators see; tested at FAT and SAT | Control engineering, with operations
Software and configuration | The code and the configuration as tested: the controller program, the HMI project, the alarm database, the network configuration | All of the above | The plant runs on it; backed up on every change | Control engineering