## Read me
Downtime log template
From Enco Group (enco.au)
What this is | A downtime log with a three-level code on every event, the duration worked out from the start and end, a code hierarchy on its own sheet to adapt, and a summary of hours by category and cause worked out from what you enter.
The time model | Calendar time: Every hour of the period. Scheduled downtime (under Calendar time): Time the plant was not meant to run: planned maintenance, shutdowns, no demand, no crew. Available time (under Calendar time): Time the plant was meant to run. Unscheduled downtime (under Available time): Time it was meant to run and did not. Operating time (under Available time): Time it ran. Breakdown (under Unscheduled downtime): Equipment failure: the maintenance share, coded by equipment and failure mode. Process (under Unscheduled downtime): Blockages, feed quality, upstream and downstream starvation and blockage, operating decisions. External (under Unscheduled downtime): Power, weather, supply, industrial, regulatory: outside the plant's control. Rate loss (under Operating time): Ran below design rate: the speed loss in OEE. Quality loss (under Operating time): Ran and produced out of specification: the quality loss in OEE.
How to use it | Decide what counts as scheduled before the first event and write it on the Codes sheet. Record every event the same shift, with times from the control system or the historian wherever they can be, and the cause chosen from the lists. Split a stop with two causes into two events. Put the work order on every breakdown. The five example rows are one day on a crushing circuit; delete them before use.
Reading it | The Summary sheet ranks hours by category and by cause for whatever is in the log. Availability is operating time over available time; take it to the OEE calculator at https://enco.au/tools/oee. The model and the codes are explained at https://enco.au/articles/downtime-tracking
Terms of use | Free to use and adapt. Provided as a starting point, without warranty.
Column | What goes in it
Start | Date and time the event began, from the historian where it can be
End | As it says
Duration (h) | Worked out from start and end
Area | As it says
Equipment | The functional location, so downtime can be read by asset
Category | The first level of the code (drop-down: Scheduled, Breakdown, Process, External)
Cause group | The second level
Cause | The third level, from the list for the group
Description | What happened, in words the next shift would understand
Work order | For a breakdown, the corrective work order
Recorded by | As it says
Shift | As it says (drop-down: Day, Night)

## Log
Start | End | Duration (h) | Area | Equipment | Category | Cause group | Cause | Description | Work order | Recorded by | Shift
2026-10-28 06:00 | 2026-10-28 06:40 |  | Crushing | CR-001 | Scheduled | No crew | Shift change | Pre-start and handover |  | A. Example | Day
2026-10-28 09:12 | 2026-10-28 10:05 |  | Crushing | CV-201 | Breakdown | Mechanical | Conveyor | Belt drift trip, tracking idler seized at the tail | WO-45120 | A. Example | Day
2026-10-28 13:30 | 2026-10-28 13:50 |  | Crushing | CR-001 | Process | Feed | Tramp | Tramp steel in the feed, crusher stopped to clear |  | A. Example | Day
2026-10-28 19:00 | 2026-10-28 23:00 |  | Crushing | CR-001 | Scheduled | Planned maintenance | Weekly PM window | Mantle inspection and liner measurement | WO-44980 | B. Example | Night
2026-10-29 02:15 | 2026-10-29 02:35 |  | Crushing | CR-001 | External | Utilities | Power outage | Site supply dipped, drives tripped, restart sequence |  | B. Example | Night
Note on A1: Date and time the event began, from the historian where it can be
Note on C1: Worked out from start and end
Note on E1: The functional location, so downtime can be read by asset
Note on F1: The first level of the code
Note on G1: The second level
Note on H1: The third level, from the list for the group
Note on I1: What happened, in words the next shift would understand
Note on J1: For a breakdown, the corrective work order

## Codes
Category | Cause group | Causes, third level (adapt to the site)
Scheduled | Planned maintenance | Weekly PM window; Shutdown; Inspection
Scheduled | No demand | No feed scheduled; Stockpile full; Market
Scheduled | No crew | Shift change; Training; Public holiday
Breakdown | Mechanical | Conveyor; Crusher; Screen; Pump; Gearbox, each by failure mode
Breakdown | Electrical | Drive; Motor; Switchgear; Protection trip; Cable
Breakdown | Instrumentation and control | Instrument fault; PLC or network; Interlock spurious
Process | Feed | No feed; Wet or sticky feed; Oversize; Tramp
Process | Blockage | Chute; Bin; Screen pegging
Process | Upstream or downstream | Starved; Blocked; Stockpile full
Process | Operating | Operator decision; Start-up; Changeover; Clean-up
External | Utilities | Power outage; Water; Air; Network
External | Environment | Weather; Lightning; Flood; Dust
External | Other | Industrial; Regulatory; Safety stand-down
Decide here what counts as scheduled, and date the decision. A breakdown is coded to the equipment that failed, by functional location. Other is not a cause.

## Summary
Hours by category and cause
Worked out from the Log. Type a cause group or cause in column A of the lower table to rank what matters at this site.
Category | Hours | Events
Scheduled
Breakdown
Process
External
Unscheduled (breakdown, process, external)
Cause group or cause | Hours | Events
Mechanical
Conveyor
Feed
Planned maintenance
A cause group and one of its causes both listed count the same hours twice. List one level at a time.