## Read me
Obsolescence register template
From Enco Group (enco.au)
What this is | A register of every item the plant depends on that a supplier could stop making or supporting: where it is used, its criticality, the supplier's life cycle status and dates, the spares held against the annual usage with the years of cover worked out, the resolution chosen, the plan, the owner and a review date.
The rule | Sort by years of cover, not by age. A thirty year old gearbox with a maker still in business is a low risk. A six year old controller whose series was discontinued, with one spare, is a high one.
How to use it | Start with the controllers, drives, networks and software, because that is where the published dates are, then the instruments, then the mechanical items with a single source. Enter the spares held and the annual usage and the years of cover is worked out. Choose a resolution that buys time and a plan that ends the problem, with a date. Review each row on its review date and each critical supplier's life cycle notices quarterly. The five example rows are a crusher branch's; delete them before use. The reasoning and IEC 62402 are at https://enco.au/articles/obsolescence-management
Terms of use | Free to use and adapt. Provided as a starting point, without warranty, and not a substitute for a site's own asset management system.
Column | What goes in it
Item | The part or product, as the supplier names it
Category | As it says (drop-down: Controller, IO and network, Drive, Instrument, Electrical, Mechanical, Software, Computer)
Make and model | As it says
Where used | The equipment tags, so the register can be read from the asset
Quantity installed | As it says
Criticality | Of the equipment it is in (drop-down: A, B, C)
Supplier status | As it says (drop-down: Active, Mature, Last time buy, End of sale, End of support, Unsupported, Unknown)
End of sale | The supplier's date, or blank
End of support | As it says
Spares held | As it says
Annual usage | Failures per year, from the history
Years of cover | Spares held divided by annual usage, worked out on the sheet
Resolution | As it says (drop-down: Last time buy, Alternative source, Repair, Successor product, Emulation or bridge, Redesign or replace, Salvage, Accept risk)
Plan | What will be done, by when, and the project or work order it sits in
Owner | As it says
Review date | As it says
Status | As it says (drop-down: Monitored, Planned, Funded, In progress, Resolved)

## Register
Item | Category | Make and model | Where used | Quantity installed | Criticality | Supplier status | End of sale | End of support | Spares held | Annual usage | Years of cover | Resolution | Plan | Owner | Review date | Status
PLC processor module, PLC-100 | Controller | Maker A, series 5 CPU | CR-001 and the area 100 feed | 2 | A | End of sale | 2024-12-31 | 2028-12-31 | 1 | 0.2 |  | Redesign or replace | Replace with the series 7 processor and IO at the 2027 shutdown; project CP-2027-04 approved. Hold the one spare until then | Control engineer | 2027-03-01 | Funded
VSD 160 kW, CV-201 drive | Drive | Maker B, model D series | CV-201-M1 | 1 | A | End of support | 2022-06-30 | 2026-06-30 | 0 | 0.1 |  | Successor product | Successor model fitted at the next CV-201 stop; new drive is a different frame, cubicle modification designed under MOC-2026-052 | Electrical engineer | 2026-12-01 | In progress
HMI server operating system | Software | Server OS, 2016 release | Control room HMI servers 1 and 2 | 2 | A | End of support |  | 2027-01-12 |  |  |  | Redesign or replace | Migrate the HMI to the supported OS release with the vendor's upgrade path; test on the standby server first | Control engineer | 2026-11-15 | Planned
Belt drift switch | Instrument | Maker C, type ZS-4 | ZS-201A, ZS-201B and 14 others | 16 | B | Last time buy | 2027-06-30 | 2030-06-30 | 3 | 1.5 |  | Alternative source | Maker D equivalent confirmed form, fit and function by the instrument engineer; approved as the standard under MOC-2026-058, no last time buy needed | Instrument engineer | 2027-06-01 | Resolved
Mechanical seal, lube oil pump | Mechanical | Maker E, cartridge seal 38 mm | CR-001-LUB-P1 and P2 | 2 | A | Unknown |  |  | 2 | 0.5 |  | Alternative source | Maker E bought out in 2025; confirm whether the cartridge is still made under the new name, and identify a second source either way | Mechanical engineer | 2026-12-01 | Monitored
A critical item past end of support with no funded plan is a finding here and a line in the risk register.
Note on A1: The part or product, as the supplier names it
Note on D1: The equipment tags, so the register can be read from the asset
Note on F1: Of the equipment it is in
Note on H1: The supplier's date, or blank
Note on K1: Failures per year, from the history
Note on L1: Spares held divided by annual usage, worked out on the sheet
Note on N1: What will be done, by when, and the project or work order it sits in

## Summary
Supplier status | Criticality A | Criticality B | Criticality C
Active
Mature
Last time buy
End of sale
End of support
Unsupported
Unknown
Open items
Counted from the register, excluding rows with status Resolved. Read the end of support rows in column B first.

## Stages
Stage | What it means | What the plant does
Active | In production, supported, the current product | Record it on the register with its criticality, and the supplier's published life cycle status if there is one
Mature | Still sold and supported, but a successor exists and the supplier's effort is moving to it | Note the successor, check whether it is a drop-in, and plan the migration before it is forced
Last time buy | The supplier announces the end of production and a date by which final orders are taken | Decide the strategy now: the lifetime buy, the alternative, or the replacement project, with the money
End of sale | No longer sold new. Repair and support continue for a published period | Hold the spares the strategy says, set up the repair route, and schedule the replacement
End of support | No repair, no firmware, no security patches, no engineering help | The replacement is due. Anything still running is on the plant's own risk, written down
Unsupported | Running on salvage, the grey market and the people who remember it | A critical item here is a finding in the register and a line in the risk register

## Resolutions
Resolution | What it is | The catch
Last time buy | Buy enough before the end of production to last to the planned replacement, plus a margin for the failure rate | Ties up money; the parts age on the shelf; the forecast has to be right
Alternative source | A second maker's equivalent, a form-fit-function replacement, or an authorised reseller's stock | Needs an engineering check that the equivalent is one; software and protocols often are not
Repair | A repair route for failed units: the maker, a specialist, or the site's own workshop with the drawings | Turnaround time has to fit the spares holding; some items cannot be repaired to the original standard
Successor product | The supplier's replacement, where it is a drop-in or close to it | Firmware, mounting, wiring and software tools change more often than the datasheet admits
Emulation or bridge | A new device that presents the old interface: a protocol gateway, a drive that accepts the old control signals | A second thing to maintain; works for interfaces, not for mechanical parts
Redesign or replace | A project to replace the equipment or the system, planned to a date | The expensive answer, and the only permanent one
Salvage | Parts from decommissioned equipment, held and tested | A stopgap with no supply behind it

## Risk factors
Factor | What it means for the risk
Criticality of what it is in | An obsolete card in a critical system is a different problem from the same card in a standby one
Support status | Where the item is on the supplier's life cycle, and whether the supplier publishes it at all
Spares held against usage | Years of cover at the current failure rate, counting the spares that will fail on the shelf
Lead time and source | Whether a replacement can be bought at all, from whom, and how long it takes
Failure rate and age | An item failing more often as it ages consumes the holding faster than the plan assumed
Skills and tools | Whether anyone can still configure it, and whether the software and the laptop that runs it still exist
Software and licences | An operating system out of support, a licence that cannot be transferred, a vendor that no longer issues keys
Interfaces | What else has to change if this does: the protocol, the wiring, the cabinet, the HMI