## Read me
Punch list template
From Enco Group (enco.au)
What this is | One punch list for the project, organised by system, with a category on every item that says what it must be closed before, an owner, a due date, a status, and separate close and verify columns. The Summary tab counts open items by system and category from what you enter.
Categories | A: Must be closed before the gate it was found at. Safety, a defect that stops the test, or anything that would be hidden by the next stage. B: Must be closed before start-up on that system, but the next stage can proceed. C: Does not affect safety or operation. Closed after handover by an agreed date.
How to use it | Walk down each system with the contractor present and list every item. Give each a category at the time it is raised. Review the list at a fixed meeting by system, open A items first. Never delete an item: close a duplicate as a duplicate and mark a disputed item disputed. The person who verifies is never the person who closed.
The stages and gates | On the Stages tab, and explained at https://enco.au/articles/commissioning-and-the-punch-list
Terms of use | Free to use and adapt. Provided as a starting point, without warranty.
Column | What goes in it
Item | A running number, never reused
System | The system or subsystem the item belongs to, from the commissioning breakdown
Tag | The equipment or location tag
Discipline | As it says (drop-down: Mechanical, Piping, Electrical, Instrumentation, Control, Civil and structural, Process)
Description | What is wrong, in enough words that someone else could find it and fix it
Category | A before the gate, B before start-up, C after handover (drop-down: A, B, C)
Raised by | As it says
Date raised | As it says
Stage found | As it says (drop-down: Construction, Pre-commissioning, Commissioning, Performance test, Handover)
Owner | The contractor or party responsible for closing it
Due | As it says
Status | As it says (drop-down: Open, In progress, Closed, Verified, Disputed)
Closed by, date | Who did the work and when
Verified by, date | Who checked it was done, which is never the person who closed it
Evidence | Photo, test record or certificate reference

## Punch list
Item | System | Tag | Discipline | Description | Category | Raised by | Date raised | Stage found | Owner | Due | Status | Closed by, date | Verified by, date | Evidence
1 | CV-201 | CV-201-M1 | Mechanical | Drive guard not fitted on the head pulley, exposed nip point | A | A. Example | 2026-10-29 | Construction | Mechanical contractor | 2026-10-30 | Open
2 | CV-201 | CV-201-ZS1 | Instrumentation | Belt drift switch wired to the pull cord input; trips as pull cord on the HMI | A | A. Example | 2026-10-29 | Pre-commissioning | E and I contractor | 2026-11-02 | Open
3 | CV-201 | CV-201 | Piping | Weeping flange on the dust suppression water line at the transfer | B | A. Example | 2026-10-29 | Pre-commissioning | Piping contractor | 2026-11-06 | Open
4 | CV-201 | CV-201 | Civil and structural | Cable tray lid missing on the walkway side, 3 m section | C | A. Example | 2026-10-29 | Commissioning | Electrical contractor | 2026-12-15 | Open
Note on A1: A running number, never reused
Note on B1: The system or subsystem the item belongs to, from the commissioning breakdown
Note on C1: The equipment or location tag
Note on E1: What is wrong, in enough words that someone else could find it and fix it
Note on F1: A before the gate, B before start-up, C after handover
Note on J1: The contractor or party responsible for closing it
Note on M1: Who did the work and when
Note on N1: Who checked it was done, which is never the person who closed it
Note on O1: Photo, test record or certificate reference

## Summary
Open items by system and category
Counts every item on the Punch list tab whose status is not Closed or Verified. Type a system in column A; the rest is worked out.
System | A open | B open | C open | Total open
CV-201
All systems
A gate is passed with no A open on the system. A B open at start-up has a date and an owner, or it is not a B.

## Stages
Stage | What it does | The gate | Punch closed
Construction complete | Built to the drawings, by system and subsystem, with the inspection and test records signed for each | Mechanical completion: the walkdown done, the records complete, the A items closed | Category A
Pre-commissioning | Static and energised checks with no process material: flushing, pressure tests, loop checks, motor solo runs, instrument calibration, interlock tests | Ready for commissioning: every system tested cold, the B items closed or scheduled | Category B on the system
Commissioning | Process material introduced, by system: functional tests, sequences, control tuning, alarm and trip tests under real conditions | Ready for start-up: the pre-startup safety review held, the operators trained, the maintenance plans live | Every A and B
Performance test | Run at rate against the guarantees: throughput, quality, availability and consumption over the agreed period | Performance accepted, or the shortfalls listed with who owns each | C items scheduled
Handover | Care, custody and control pass to operations, with the documents, the spares, the data and the open items | Acceptance: operations sign that they have what they need to run and maintain it | C items by agreed dates