## Read me
Shutdown planning checklist
Readiness by phase and gate, from Enco Group (enco.au)
What this is
A readiness checklist for a planned shutdown, turnaround or outage, organised by phase. Each phase ends at a gate, and each line says what has to be true and what proves it.
The method behind it, from scope challenge to close-out, is in the shutdown planning guide at https://enco.au/articles/shutdown-planning-guide
How to use it
1. On the Checklist tab, give every line an owner and a due date at the start of the event's planning.
2. Close a line only when the evidence exists. A percentage complete is not evidence; a signed document, a kitting report or a purchase order is.
3. Do not open the next phase until every line in the phase before it is closed or has a documented exception.
4. Use the Scope register tab from the first candidate item. Record the source, the justification and the challenge decision for every line.
5. After the freeze, every addition goes on the Addition log with its approver and its effect on the critical path. Scope growth at close-out is the additions as a share of the frozen scope.
Adapting it
The windows suit a quarterly or annual processing plant shutdown. Shorten them for a short stop and lengthen them for a refinery turnaround; keep the order of the gates.
Terms of use
Free to use and adapt. Provided as a starting point, without warranty, and not a substitute for a site's own safety, permit and isolation systems.

## Checklist
Shutdown planning checklist
Close each line with evidence. Do not open the next phase until the gate behind it is closed.
# | Phase | Window | What has to be true | What proves it | Owner | Due | Status | Notes
STRATEGY · T minus 12 to 9 months · gate: Event approved
1 | Strategy | T minus 12 to 9 months | Event dates, duration and the production plan it sits inside agreed with operations | Approved event calendar |  |  | Open
2 | Strategy | T minus 12 to 9 months | Budget envelope and the business case for the event set | Approved budget |  |  | Open
3 | Strategy | T minus 12 to 9 months | Shutdown manager, planning lead and scope owners named | Roles on the organisation chart |  |  | Open
4 | Strategy | T minus 12 to 9 months | Long lead items identified from the strategy tasks due in the window | Long lead list with order dates |  |  | Open
SCOPE DEVELOPMENT · T minus 9 to 6 months · gate: Scope challenged
5 | Scope development | T minus 9 to 6 months | Every candidate item of work collected into one list with a source and a justification | Scope register |  |  | Open
6 | Scope development | T minus 9 to 6 months | Wear parts measured and intervals checked, so scope rests on condition rather than habit | Wear measurements on the register |  |  | Open
7 | Scope development | T minus 9 to 6 months | Each item challenged: can it be done online, deferred to the next event, or must it be done now | Challenge decision recorded per item |  |  | Open
8 | Scope development | T minus 9 to 6 months | Projects and capital work that want the window declared and integrated | Project scope on the register |  |  | Open
9 | Scope development | T minus 9 to 6 months | Scope that failed the challenge removed or deferred with a reason | Deferral log |  |  | Open
SCOPE FREEZE · T minus 6 to 4 months · gate: Scope frozen
10 | Scope freeze | T minus 6 to 4 months | The frozen scope signed by operations, maintenance and the shutdown manager | Signed freeze document |  |  | Open
11 | Scope freeze | T minus 6 to 4 months | The addition process after the freeze defined: who approves, on what evidence, against what consequence | Addition process issued |  |  | Open
12 | Scope freeze | T minus 6 to 4 months | Long lead materials ordered against the frozen scope | Purchase orders with delivery dates before staging |  |  | Open
13 | Scope freeze | T minus 6 to 4 months | Contract packages scoped from the frozen list and tendered | Packages issued |  |  | Open
DETAILED PLANNING · T minus 6 to 2 months · gate: Plan complete
14 | Detailed planning | T minus 6 to 2 months | Every work order has a job pack: steps, trades, durations, materials, permits, isolations and access | Job packs approved |  |  | Open
15 | Detailed planning | T minus 6 to 2 months | Isolations grouped and the isolation plan drafted | Isolation list and plan |  |  | Open
16 | Detailed planning | T minus 6 to 2 months | Scaffold, cranes, lifts and access designed and booked | Access plan and bookings |  |  | Open
17 | Detailed planning | T minus 6 to 2 months | Schedule built from the job packs, critical path identified, resources levelled | Baseline schedule with critical path |  |  | Open
18 | Detailed planning | T minus 6 to 2 months | Shift pattern, crew sizes and contractor numbers set against the schedule | Resource histogram |  |  | Open
19 | Detailed planning | T minus 6 to 2 months | Contingency held as time and money, with the rule for spending it | Contingency on the schedule and budget |  |  | Open
20 | Detailed planning | T minus 6 to 2 months | Start-up and recommissioning sequence planned with operations | Start-up plan |  |  | Open
READINESS AND STAGING · T minus 2 months to T · gate: Ready to execute
21 | Readiness and staging | T minus 2 months to T | Materials received, inspected, kitted by work order and staged | Kitting report, nothing outstanding on the critical path |  |  | Open
22 | Readiness and staging | T minus 2 months to T | Contractors mobilised, inducted and competent on the site's permit and isolation systems | Induction and competency records |  |  | Open
23 | Readiness and staging | T minus 2 months to T | Permits pre-written and isolations pre-approved for the first shifts | Permit and isolation packs |  |  | Open
24 | Readiness and staging | T minus 2 months to T | Pre-shutdown work done online: scaffold up, pre-assembly complete, lay down areas set | Pre-shutdown checklist closed |  |  | Open
25 | Readiness and staging | T minus 2 months to T | Daily meeting, reporting and change control rehearsed with the people who will run them | Meeting rhythm issued |  |  | Open
26 | Readiness and staging | T minus 2 months to T | Safety plan, emergency arrangements and simultaneous operations reviewed | Safety plan approved |  |  | Open
EXECUTION · T to the end of the window · gate: Plant handed back
27 | Execution | T to the end of the window | Progress measured against the baseline every shift, by work order | Shift progress report |  |  | Open
28 | Execution | T to the end of the window | Every addition after the freeze goes through the addition process and is counted | Addition log with approvals |  |  | Open
29 | Execution | T to the end of the window | Critical path reviewed every shift and recovery decided when it slips | Critical path status in the daily meeting |  |  | Open
30 | Execution | T to the end of the window | Findings during the work (discovered scope) assessed for now, later or never | Discovery log |  |  | Open
31 | Execution | T to the end of the window | Quality checks and tests signed before any item is closed | Inspection and test records |  |  | Open
CLOSE-OUT · T plus 2 to 6 weeks · gate: Event closed
32 | Close-out | T plus 2 to 6 weeks | Punch list cleared or converted to work orders with owners | Punch list closed |  |  | Open
33 | Close-out | T plus 2 to 6 weeks | Work order history, measurements and as-found condition recorded in the CMMS | History complete on every work order |  |  | Open
34 | Close-out | T plus 2 to 6 weeks | Wear life achieved fed back into intervals and the next event's scope | Interval changes logged |  |  | Open
35 | Close-out | T plus 2 to 6 weeks | Duration, cost, scope growth, safety and start-up performance reported against plan | Close-out report |  |  | Open
36 | Close-out | T plus 2 to 6 weeks | Lessons captured and the first items for the next event registered | Lessons register and the next scope register opened |  |  | Open

## Scope register
Scope register
Every candidate item, its source and justification, and the challenge decision.
ID | Equipment | Work | Source | Justification (evidence) | Must / should / could | Challenge decision | Est. hours | Est. cost | Owner | Notes

## Addition log
Addition log
Everything added after the scope freeze. Scope growth = added hours over frozen hours.
ID | Date | Equipment | Work | Source | Approver | Est. hours | Decision | Effect on critical path | Reason | Frozen scope hours | 0
Approved added hours
Scope growth