## Read me
Weekly maintenance schedule template
The weekly cycle in one workbook, from Enco Group (enco.au)
What this is
A template for a frozen weekly maintenance schedule: capacity by trade, the schedule by day and work order, a break-in log, and the measures worked out from what you enter.
The cycle, the roles and the measures are explained in the planning and scheduling guide at https://enco.au/articles/maintenance-planning-and-scheduling
The weekly cycle
Week before, Monday: Capacity set (Supervisors). Available hours by trade for the coming week, after leave, training and standing commitments.
Week before, Tuesday: Draft schedule built (Scheduler). Ready-to-schedule work loaded to the capacity, in priority order, with the PM program first.
Week before, Wednesday: Operations alignment (Scheduler and operations). Equipment access and production windows confirmed against the draft.
Week before, Thursday: Schedule review meeting (Maintenance superintendent). Conflicts resolved, the schedule agreed by operations, maintenance and the planner.
Week before, Friday: Schedule frozen (Maintenance superintendent). The frozen schedule issued. Anything added after this is break-in work.
Execution week, Daily: Daily schedule and break-in control (Supervisors). Each day's work assigned by person, break-in requests through the one approval path.
Execution week, Daily: Progress and feedback (Tradespeople and supervisors). Work orders closed with hours, findings and job plan feedback the same day.
Week after, Monday: Compliance review (Planner and superintendent). Schedule compliance, break-in share and the reasons for every miss, fed into next week's draft.
How to use it
1. Capacity tab: enter the hours actually available next week for each trade, after leave, training and standing commitments.
2. Schedule tab: list ready work orders by day, with trade, people and hours each. Loaded hours by trade are compared with capacity at the top of the Capacity tab.
3. Freeze the schedule on the agreed day. From then on, new work goes on the Break-in log, not the Schedule tab.
4. During the week, mark each scheduled job done as scheduled (Y or N) and record the reason for any N.
5. The Measures tab works out schedule compliance and break-in share for the week, the same way the calculator does.
Check a week against the Schedule Compliance Calculator at https://enco.au/tools/schedule-compliance
Terms of use
Free to use and adapt. Provided as a starting point, without warranty.

## Capacity
Capacity by trade
Hours actually available next week, and the hours the schedule loads against them.
Trade | People | Hours each | Less: leave, training, meetings | Available hours | Scheduled hours
Mechanical | 0 | 0 | 0
Electrical | 0 | 0 | 0
Instrumentation | 0 | 0 | 0
Boilermaker | 0 | 0 | 0
Operator assist | 0 | 0 | 0
Total
Loading
Aim to load no more than the available hours. Over 100% is a schedule that cannot be met.

## Schedule
Weekly schedule
Ready work only. Frozen on the agreed day; anything after that goes on the Break-in log.
Day | Work order | Equipment | Description | Priority | Trade | People | Hours each | Total hours | Status | Done as scheduled | Reason not done

## Break-in log
Break-in log
Work added after the freeze. Each line approved through the one path, with the job it displaced.
Day | Work order | Equipment | Description | Trade | People | Hours each | Total hours | Approved by | Displaced work order | Reason (reliability, planning, discipline)

## Measures
The week's measures
Worked out from the Schedule and Break-in tabs, the same way the Schedule Compliance Calculator does.
Scheduled hours (frozen schedule)
Scheduled hours done as scheduled
Schedule compliance
Break-in hours (added after the freeze)
Hours worked (done as scheduled plus break-in)
Break-in share
Read the two together. High compliance with high break-in means the plan was small. Low compliance with low break-in means the plan was not ready.